## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | Meowilla |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Hao Nguyen |  |  | 2025-02-12 | 2025-03-23 | 0% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
No | SPRINT 1 |  | Hao Nguyen |  | 2025-02-12 | 2025-02-25 | 14
No | Website Header | FE | Hao Nguyen | 5 | 2025-02-12 | 2025-02-25 | 14 | In Progress
No | Website Footer | FE | Hao Nguyen | 5 | 2025-02-12 | 2025-02-25 | 14 | On Hold
No | Design back end for user management | BE | Hao Nguyen | 13 | 2025-02-12 | 2025-02-25 | 14 | On Hold
No | SPRINT 2 |  | Hao Nguyen |  | 2025-02-25 | 2025-03-10 | 14
No | Media browsing | FE | Hao Nguyen | 3 | 2025-02-25 | 2025-03-10 | 14 | On Hold
No | User registration | FE + BE | Hao Nguyen | 13 | 2025-02-25 | 2025-03-10 | 14 | On Hold
No | Intergrate API for Header | FE | Hao Nguyen | 5 | 2025-02-25 | 2025-03-10 | 14 | On Hold
No | Intergrate API for Footer | FE | Hao Nguyen | 5 | 2025-02-25 | 2025-03-10 | 14 | On Hold
No | Play the media | FE | Hao Nguyen | 3 | 2025-02-25 | 2025-03-10 | 14 | On Hold
No | SPRINT 3 |  | Hao Nguyen |  | 2025-03-10 | 2025-03-23 | 14
No | Search and filter for media | FE | Hao Nguyen | 8 | 2025-03-10 | 2025-03-23 | 14 | On Hold
No | Containerisation the website | DevOps | Hao Nguyen | 13 | 2025-03-10 | 2025-03-23 | 14 | On Hold
No | Integration with Openverse API | FE | Hao Nguyen | 13 | 2025-03-10 | 2025-03-23 | 14 | On Hold
No | SPRINT 4 |  | Hao Nguyen |  | 2025-03-23 | 2025-04-05 | 14
No | Make automated building strategy and automated testing strategy | DevOps | Hao Nguyen | 21 | 2025-03-23 | 2025-04-05 | 14 | On Hold
No | Deploy the website | DevOps | Hao Nguyen | 13 | 2025-03-23 | 2025-04-05 | 14 | On Hold
Formulas:
END DATE = MAX([END DATE, row below]:H15)
START DATE = MIN([START DATE, row below]:G22)

## Dropdown Keys - Do Not Delete - (hidden)
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold